## TASKS
ZUET - Work Plan
OUR TASKS | START DATE | DUE DATE | % COMPLETE | DONE | NOTES
Setting Up Exersies that the user will make | 2017-05-30 | 2017-05-31 | 75% | 0 | Search for a few more and make sure the rutine makes sense for a person starting. - Rafael
Make the timer for the exercise | 2017-05-31 | 2017-06-01 | 75% | 0 | Highly important, primary feature. - Yessy
search for a play button and make it work | 2017-05-31 | 2017-05-31 | 0% | 0 | Make it be present in a normal state, when pressed the pause button will appear and the timer MUST start. - Rafael
let the user add different rutines | 2017-06-02 | 2017-06-05 | 0% | 0 | Important, lets the user feel part of the app expirience. - Rafael
Enseñar las como hacer los ejercicios de las rutinas al usuario. | 2017-06-02 | 2017-06-05 | 0% | 0 | Important, lets the user feel part of the app expirience. - Yessy